# The Renewable Energy Development Handbook: Diligence Checklists

Julian R. Sterling. Appendix B of the book in editable form: tick each box as the item is reviewed.

These checklists gather the questions raised in the chapters, in the order a buyer at notice to proceed would work through them. They are a starting point for a diligence plan, not a substitute for specialist advisers; every rule cited carries its date.

## B.1 Land and site control

☐  Option and lease agreements for every parcel, signed by every owner of record, with the project company (or an assignee it controls) as tenant.

☐  Option term, exercise notice and payments made; lease term, extensions, rent and escalation, as described in chapter 3.

☐  Site control at the level FERC Order No. 2023 (28 July 2023) requires at the interconnection request and, in full, at the facilities study.

☐  Assignment rights without landowner consent to a buyer, an affiliate or a lender; leasehold mortgage and lender cure rights; estoppel certificates.

☐  Crop, grazing and access rights kept by the landowners.

☐  Decommissioning obligations in the lease, consistent with the county permit and its security.

☐  Title commitments, surveys and curative work completed (mortgages subordinated, mineral rights addressed).

☐  Gen-tie easements for every crossing.

☐  Side letters and promises to landowners or neighbors made outside the documents.

## B.2 Resource and energy yield

☐  Source and period of the irradiance or wind data; satellite, ground station or met mast; correlation to the long-term record (chapter 4).

☐  Independent energy yield assessment, its date and the layout it assumes.

☐  Loss waterfall line by line: soiling and snow, shading, temperature, mismatch and wiring, inverter efficiency, clipping at the loading ratio, AC losses, availability.

☐  Uncertainty components and how they combine for one-year and ten-year exceedance levels.

☐  P50, P90 and P99 values, and which ones the lender and the PPA counterparty rely on.

☐  For wind: shear, wake losses from neighboring projects, power curve warranty, icing and curtailment for wildlife or radar.

☐  The same energy figure in the model, the PPA, the EPC guarantee and the lender's case.

## B.3 Permits and environmental

☐  Every local, state and federal permit, with its conditions, appeal period and expiry (chapter 5).

☐  Conditional use permit conditions: setbacks, vegetative screening, decommissioning security, road use agreement; evidence each can be met.

☐  Environmental surveys and their seasons: wetlands, cultural resources, threatened and endangered species habitat.

☐  Federal triggers: wetlands permits, species consultation, federal land or funding, aviation; for wind, FAA and Department of Defense review, and the status of the injunction of 6 August 2026 against the review freeze (as of October 2026).

☐  Hearing record, opposition, pending litigation, local moratoriums.

☐  State siting thresholds and whether the project falls under them; permits transferable to a buyer.

## B.4 Interconnection

☐  Queue position, cluster and study stage; request in the project company's name (chapter 6).

☐  Study deposits, readiness deposits and LGIA security posted, and who funded them.

☐  Withdrawal penalties and the exemptions for large cost increases under Order No. 2023.

☐  Network upgrades assigned: estimate, firmness, cost allocation, and reallocation risk if cluster mates withdraw; affected system study results.

☐  Facilities study and LGIA: milestones, transmission owner schedule for its work, consequences of its delay, operating limits.

☐  Interconnection service: energy only or deliverable for capacity, and the accredited capacity that results.

## B.5 Offtake (utility PPA and virtual PPA)

### Utility PPA

☐  Products sold (energy, RECs, capacity), price, escalation and term (chapter 7).

☐  Delivery point and who carries the basis between node and hub.

☐  Commercial operation deadline, PPA delay damages and termination rights; how they line up with the EPC schedule.

☐  Output or availability guarantees and shortfall damages; who pays for curtailment.

☐  Change in law, credit support and consent to assignment or sale.

### Virtual PPA

☐  Strike price, term, settlement hub and settlement method (as-generated or fixed shape).

☐  Hours settled, treatment of negative prices, and the basis the project keeps.

☐  REC delivery and registry; the buyer's accounting needs, including any hourly matching requirement under the GHG Protocol Scope 2 revision (draft October 2025, final rules expected around the end of 2027, as of October 2026).

☐  Buyer credit, collateral and termination payments.

## B.6 Equipment, supply and foreign entity documentation

☐  Module, tracker and inverter supply agreements: price and adjustments, delivery schedule and delay damages, factory and site tests, title and risk transfer (chapter 8).

☐  Warranties: term, degradation curve, remedies, warrantor's credit.

☐  Origin of cells, wafers and modules; customs entries; forced labor documentation.

☐  Tariff exposure at signing and the contract allocation of new duties: Section 232 polysilicon tariff effective 4 December 2026, antidumping and countervailing duty orders, Section 301 duties effective 24 July 2026 (all as of October 2026).

☐  Supplier certificates supporting the material assistance cost ratio, the method used (actual costs or the safe harbor tables under Notice 2026-15 of 12 February 2026), and the de minimis analysis.

☐  Supplier ownership, debt and licenses: no prohibited foreign entity, no effective control.

## B.7 EPC

☐  Structure: full wrap, split EPC and balance of plant, or owner-furnished equipment, and the interfaces each creates (chapter 9).

☐  Fixed price, owner's contingency, change order triggers.

☐  Schedule and the conditions for mechanical and substantial completion.

☐  Delay damages: daily rate, cap, and whether they cover the owner's lost margin, deferred credits and PPA damages.

☐  Performance tests and buy-down damages; the tested capacity threshold.

☐  Liability cap, retention, letters of credit or parent guarantees; change in law and tariff allocation.

☐  Prevailing wage and apprenticeship obligations flowed down to every subcontractor, with records.

## B.8 Tax credits

### Beginning of construction file

☐  Date construction began and the method relied on: physical work of a significant nature on or off site under a binding written contract, or the five percent safe harbor restored when Notice 2025-42 was vacated on 6 June 2026 (as of October 2026, subject to any appeal or new guidance; chapter 11).

☐  Evidence the start came on or before 4 July 2026 (contracts, invoices, photographs, manufacturer records); otherwise, a plan to be placed in service by 31 December 2027.

### Continuity

☐  Continuous program of work since the start, documented month by month.

☐  Placed in service deadline under the continuity safe harbor (end of the fourth calendar year after the year construction began).

### Prevailing wage and apprenticeship

☐  Payroll records for every contractor, wage determinations used, apprenticeship hours, cure procedures for any gap.

### Credit choice and bonuses

☐  PTC or ITC election and the reasoning; eligible basis and exclusions for the ITC.

☐  Energy community qualification under the current annual update (Notice 2026-39 of 10 June 2026); domestic content support.

☐  Material assistance cost ratio result against the threshold for the year construction began.

### Transfer documents

☐  Transfer agreement: buyer, price, payment timing, indemnities, tax insurance; registration and election filings; ITC recapture exposure during the five years after placed in service (disposition of the property or a change in use) and which party bears it under the transfer agreement.

## B.9 Financing and closing at NTP

☐  Purchase agreement: premium, reimbursement, milestone payments, conditions precedent, representations and indemnities (chapter 14).

☐  Every project contract assignable to the buyer and its lenders; consents obtained.

☐  Construction loan term sheet; term debt sizing on P50 and P99 with the coverage ratios by offtake; tax equity or transfer bridge terms (chapter 12).

☐  Model inputs traced to signed contracts; discount rates by risk; credits at transfer price.

## B.10 Construction to COD

☐  Construction schedule against the PPA deadline and the credit deadline, with float identified (chapter 15).

☐  Substation energization, backfeed and testing plan agreed with the transmission owner.

☐  Commissioning and capacity test procedures identical across the EPC contract, the supply agreements and the PPA.

☐  Placed in service date documented for tax; commercial operation date documented under the PPA; the two kept distinct.

☐  Punch list, final completion, release of retention; delay log with damages claimed and paid.

☐  Handover package: as-built drawings, warranties, spares, O&M and asset management agreements.

Julian R. Sterling, The Renewable Energy Development Handbook. Starting points for a diligence plan, not a substitute for specialist advisers. Every rule cited carries its date; check it is still current.